## Sheet1
Sr # | Date | Time | Activity Details | O365 team | IT support | status | Remarks
1 |  |  | Get RS Mail account credentials form user.
2 |  |  | Create mailbox with Fname.Lname@synechron.com on O365, activate license as per rule. (O365 Admin Task)
3 |  |  | Start Backend migration. (O365 Admin Task)
4 |  |  | Check backend migration status -Completed
5 |  |  | Set Email Forward from Racxkspace mailbox to O365 Mailbox (Only Sr Management for sager side)
6 |  |  | Visit end user desktop/take remote session.
7 |  |  | Take Backup contacts, Calendar, Notes, tasks, Rules and missing mail items to PST.
8 |  |  | Do not delete mailbox from Rackspace. |  |  |  | Will keep as it is till Rackspace email service live
9 |  |  | Verify/re-add in respective DLs, GLs. For RS and O365
10 |  |  | Un-install exiting Office, note down existing office version ...
11 |  |  | Install and activate O365 Office Pro plus (Refer O365 offline installation help doc).
12 |  |  | Verify/configure Registry entries for O365 mail account configure. (use local xml re-direction for Autodiscover).
13 |  |  | Configure Outlook pointing to O365 Mailbox.
14 |  |  | Import/Copy - contacts, Calendar, Notes, tasks, Rules and missing mail items (Inbox/Sent).
15 |  |  | Verify Email Signature
16 |  |  | Configure/Update Email account on user Mobile device.
17 |  |  | Verify mail send/receive.
18 |  |  | Configure/Test Skype for business( E3, E1 users)
19 |  |  | Educate O365 Webmail access.
20 |  |  | Get confirmation from end user on mail...